## Test Overview
CAMELLIA + REDIS - PRODUCTION TEST PLAN
Project: | Redis Multi-Pool Architecture with Camellia Proxy
Test Lead: | Infrastructure Team
Created Date: | 2026-03-30
Environment: | Lab/Staging
Version: | Camellia 1.3.x + Redis 7.2.x
TEST SUMMARY
Category | Total Tests | Passed | Failed | Blocked | Not Run | Pass Rate | Status
Basic Commands | 25 | 0 | 0 | 0 | 25 | 0% | FAIL
Multi-key Operations | 15 | 0 | 0 | 0 | 15 | 0% | FAIL
Sharding & Routing | 20 | 0 | 0 | 0 | 20 | 0% | FAIL
Multi-tenancy | 12 | 0 | 0 | 0 | 12 | 0% | FAIL
Rate Limiting | 10 | 0 | 0 | 0 | 10 | 0% | FAIL
Hot Key Caching | 8 | 0 | 0 | 0 | 8 | 0% | FAIL
Failover & HA | 15 | 0 | 0 | 0 | 15 | 0% | FAIL
Performance | 10 | 0 | 0 | 0 | 10 | 0% | FAIL
Security | 8 | 0 | 0 | 0 | 8 | 0% | FAIL
Operations | 12 | 0 | 0 | 0 | 12 | 0% | FAIL
TOTAL | 135 | 0 | 0 | 0 | 135 | 0%

## 1. Basic Commands
ID | Test Case | Category | Command | Expected Result | Actual Result | Status | Priority | Tester | Date | Notes
TC-001 | SET basic string value | String | SET key1 "value1" | +OK |  | Not Run | P1
TC-002 | GET existing key | String | GET key1 | "value1" |  | Not Run | P1
TC-003 | GET non-existent key | String | GET nonexist | (nil) |  | Not Run | P2
TC-004 | DEL existing key | String | DEL key1 | (integer) 1 |  | Not Run | P1
TC-005 | EXPIRE set TTL | String | SETEX temp 10 "value" | +OK |  | Not Run | P1 |  |  | TTL 10 seconds
TC-006 | TTL check remaining time | String | TTL temp | (integer) 10 |  | Not Run | P2
TC-007 | INCR counter | String | INCR counter | (integer) 1 |  | Not Run | P1
TC-008 | INCRBY increment by N | String | INCRBY counter 5 | (integer) 6 |  | Not Run | P1
TC-009 | DECR counter | String | DECR counter | (integer) 5 |  | Not Run | P2
TC-010 | APPEND string | String | APPEND key1 "append" | (integer) length |  | Not Run | P2
TC-011 | HSET hash field | Hash | HSET user:1 name "John" | (integer) 1 |  | Not Run | P1
TC-012 | HGET hash field | Hash | HGET user:1 name | "John" |  | Not Run | P1
TC-013 | HGETALL all fields | Hash | HGETALL user:1 | All key-value pairs |  | Not Run | P1
TC-014 | HDEL delete field | Hash | HDEL user:1 name | (integer) 1 |  | Not Run | P2
TC-015 | LPUSH list left | List | LPUSH mylist "item1" | (integer) 1 |  | Not Run | P1
TC-016 | RPUSH list right | List | RPUSH mylist "item2" | (integer) 2 |  | Not Run | P1
TC-017 | LPOP pop left | List | LPOP mylist | "item1" |  | Not Run | P1
TC-018 | RPOP pop right | List | RPOP mylist | "item2" |  | Not Run | P1
TC-019 | LRANGE get range | List | LRANGE mylist 0 -1 | All items |  | Not Run | P2
TC-020 | SADD set member | Set | SADD myset "member1" | (integer) 1 |  | Not Run | P1
TC-021 | SMEMBERS all members | Set | SMEMBERS myset | All members |  | Not Run | P1
TC-022 | SISMEMBER check member | Set | SISMEMBER myset "member1" | (integer) 1 |  | Not Run | P2
TC-023 | ZADD sorted set | Sorted Set | ZADD rank 100 "user1" | (integer) 1 |  | Not Run | P1
TC-024 | ZRANGE get range | Sorted Set | ZRANGE rank 0 -1 | Members by score |  | Not Run | P1
TC-025 | EXISTS check key | Generic | EXISTS key1 | (integer) 0 or 1 |  | Not Run | P2

## 2. Multi-key Ops
ID | Test Case | Category | Command | Expected Result | Actual Result | Status | Priority | Tester | Date | Notes
TC-101 | MGET multiple keys same shard | MGET | MGET {user}:1 {user}:2 | Values for both keys |  | Not Run | P1 |  |  | Use hash tag {user}
TC-102 | MGET without hash tag (cross-shard) | MGET | MGET user:1 user:2 | Should work via proxy |  | Not Run | P1 |  |  | May be slower
TC-103 | MSET multiple keys same shard | MSET | MSET {user}:1 "a" {user}:2 "b" | +OK |  | Not Run | P1
TC-104 | MSET without hash tag | MSET | MSET user:3 "c" user:4 "d" | +OK or Error |  | Not Run | P2 |  |  | Check Camellia support
TC-105 | DEL multiple keys same shard | DEL | DEL {user}:1 {user}:2 | (integer) 2 |  | Not Run | P1
TC-106 | SINTER set intersection same shard | Set | SINTER {set}:1 {set}:2 | Common members |  | Not Run | P1
TC-107 | SUNION set union same shard | Set | SUNION {set}:1 {set}:2 | All unique members |  | Not Run | P1
TC-108 | SDIFF set difference same shard | Set | SDIFF {set}:1 {set}:2 | Difference |  | Not Run | P2
TC-109 | SINTER cross-shard (should fail) | Set | SINTER set:1 set:2 | Error |  | Not Run | P1 |  |  | Must use hash tags
TC-110 | ZINTERSTORE sorted sets same shard | Sorted Set | ZINTERSTORE out 2 {z}:1 {z}:2 | (integer) count |  | Not Run | P1
TC-111 | ZUNIONSTORE sorted sets | Sorted Set | ZUNIONSTORE out 2 {z}:1 {z}:2 | (integer) count |  | Not Run | P2
TC-112 | RENAME key same shard | Generic | RENAME {key}:old {key}:new | +OK |  | Not Run | P1
TC-113 | RENAMENX if not exists | Generic | RENAMENX {key}:1 {key}:2 | (integer) 1 or 0 |  | Not Run | P2
TC-114 | Pipeline MGET performance | Pipeline | Pipeline 100 MGET commands | All responses |  | Not Run | P1 |  |  | Test pipelining
TC-115 | Transaction MULTI/EXEC same shard | Transaction | MULTI; SET {t}:1 v; GET {t}:1; EXEC | Atomic execution |  | Not Run | P1 |  |  | Check support

## 3. Sharding & Routing
ID | Test Case | Category | Command | Expected Result | Actual Result | Status | Priority | Tester | Date | Notes
TC-201 | Key routing to correct pool | Routing | SET test:key:1 "value" | Routes to Pool 1 |  | Not Run | P1 |  |  | Verify via pool monitoring
TC-202 | Hash slot calculation | Routing | Calculate slot for key "user:100" | Correct bucket (0-1023) |  | Not Run | P1 |  |  | Check hash function
TC-203 | Consistent hashing stability | Routing | Same key multiple times | Always same pool |  | Not Run | P1 |  |  | 100 iterations
TC-204 | Hash tag extraction | Routing | Key: {user}:profile:123 | Hash on "user" only |  | Not Run | P1 |  |  | Verify hash tag logic
TC-205 | Multiple hash tags (first wins) | Routing | Key: {user}:{session}:data | Hash on "user" |  | Not Run | P2 |  |  | First tag precedence
TC-206 | No hash tag - full key hash | Routing | Key: user:session:123 | Hash full string |  | Not Run | P2
TC-207 | Empty hash tag handling | Routing | Key: {}:data | Error or hash full key |  | Not Run | P2
TC-208 | Pool distribution uniformity | Distribution | Insert 10000 random keys | Even distribution ±10% |  | Not Run | P1 |  |  | Statistical test
TC-209 | Bucket 0 routing | Edge Case | Key that hashes to bucket 0 | Routes to Pool 1 |  | Not Run | P2
TC-210 | Bucket 1023 routing | Edge Case | Key that hashes to bucket 1023 | Routes to Pool 10 |  | Not Run | P2
TC-211 | Routing config hot reload | Config | Update dashboard config | Proxies reload in 5s |  | Not Run | P1 |  |  | Check poll interval
TC-212 | Invalid pool endpoint handling | Error | Pool down temporarily | Error message to client |  | Not Run | P1
TC-213 | Fallback to local config | Failover | Dashboard unreachable | Use last good config |  | Not Run | P1 |  |  | Proxy resilience
TC-214 | Cross-pool key migration | Migration | Change key routing | Key accessible at new pool |  | Not Run | P1 |  |  | Rebalancing scenario
TC-215 | SCAN command across shards | SCAN | SCAN 0 MATCH user:* | Returns keys from all pools |  | Not Run | P1 |  |  | Camellia feature
TC-216 | KEYS command (if supported) | KEYS | KEYS user:* | All matching keys or Error |  | Not Run | P2 |  |  | Should be blocked
TC-217 | Read/Write split routing | R/W Split | Configure read from replica | GET routes to replica |  | Not Run | P1 |  |  | If enabled
TC-218 | Write always to master | R/W Split | SET command | Always routes to master |  | Not Run | P1
TC-219 | Dual-write configuration | Dual-write | Write to 2 pools simultaneously | Both pools have data |  | Not Run | P1 |  |  | Migration feature
TC-220 | Bucket reallocation | Operations | Add Pool 11, rebalance | Traffic redistributed |  | Not Run | P1 |  |  | Operations test

## 4. Multi-tenancy
ID | Test Case | Category | Command | Expected Result | Actual Result | Status | Priority | Tester | Date | Notes
TC-301 | Connect with tenant password | Auth | AUTH service-group-1-password | +OK |  | Not Run | P1
TC-302 | Route to tenant-specific pools | Routing | SET key1 "value" (tenant-1) | Routes to Pool 1 |  | Not Run | P1 |  |  | Based on bid/bgroup
TC-303 | Tenant isolation - different pools | Isolation | Tenant-1 and Tenant-2 keys | Different pools |  | Not Run | P1
TC-304 | Invalid tenant password | Auth | AUTH wrong-password | Error: invalid password |  | Not Run | P1
TC-305 | No password authentication | Auth | Connect without AUTH | Error: auth required |  | Not Run | P1
TC-306 | Dashboard config per tenant | Config | Different sharding for tenant-2 | Correct routing |  | Not Run | P1 |  |  | bid/bgroup mapping
TC-307 | Tenant namespace plugin | Plugin | Key: user:1 (tenant-1) | Stored as tenant1:user:1 |  | Not Run | P2 |  |  | If enabled
TC-308 | Rate limit per tenant | Rate Limit | Exceed tenant-1 limit | Throttled, tenant-2 ok |  | Not Run | P1 |  |  | Isolation
TC-309 | IP whitelist per tenant | Security | Access from allowed IP | Success |  | Not Run | P1
TC-310 | IP blacklist enforcement | Security | Access from blocked IP | Connection refused |  | Not Run | P1
TC-311 | Tenant config update | Config | Update tenant-1 pools in dashboard | Applied in 5s |  | Not Run | P1 |  |  | Hot reload
TC-312 | Add new tenant dynamically | Operations | Create tenant-11 config | Immediately available |  | Not Run | P1 |  |  | No proxy restart

## 5. Performance
ID | Test Case | Metric | Target | Actual | Status | Priority | Threads | Duration | Tester | Date | Notes
TC-501 | GET throughput (QPS) | QPS | 100000 |  | Not Run | P1 | 10 | 60s |  |  | 70% read
TC-502 | SET throughput (QPS) | QPS | 80000 |  | Not Run | P1 | 10 | 60s |  |  | 30% write
TC-503 | Mixed workload QPS | QPS | 150000 |  | Not Run | P1 | 20 | 60s |  |  | 70/30 read/write
TC-504 | GET latency avg | Latency (ms) | <0.5 |  | Not Run | P1 | 10 | 60s
TC-505 | GET latency p99 | Latency (ms) | <2 |  | Not Run | P1 | 10 | 60s
TC-506 | SET latency avg | Latency (ms) | <0.8 |  | Not Run | P1 | 10 | 60s
TC-507 | Proxy overhead vs direct | Overhead % | <5% |  | Not Run | P1 | 10 | 60s |  |  | Compare with direct Redis
TC-508 | Pipeline performance | QPS | 500000 |  | Not Run | P1 | 10 | 60s |  |  | 100 commands per pipeline
TC-509 | Connection pool efficiency | Connections | <200 |  | Not Run | P2 | 50 | 60s |  |  | To backend Redis
TC-510 | Memory usage under load | Memory (GB) | <12 |  | Not Run | P1 | 20 | 300s |  |  | Proxy JVM heap

## 6. Failover & HA
ID | Test Case | Category | Command | Expected Result | Actual Result | Status | Priority | Tester | Date | Notes
TC-601 | Redis master failover | Failover | Kill Redis master | Sentinel promotes replica <10s |  | Not Run | P1 |  |  | Automatic failover
TC-602 | Proxy detects new master | Discovery | After master failover | Proxy routes to new master |  | Not Run | P1 |  |  | Via Sentinel
TC-603 | Client reconnection | Resilience | During failover | Clients retry, <10s downtime |  | Not Run | P1
TC-604 | No data loss during failover | Data Integrity | Check keys after failover | All keys present |  | Not Run | P1 |  |  | AOF/RDB sync
TC-605 | Sentinel quorum failover | Sentinel | 2/3 sentinels agree | Failover triggered |  | Not Run | P1
TC-606 | Sentinel quorum loss | Sentinel | Only 1/3 sentinels up | No failover (safe) |  | Not Run | P1 |  |  | Prevent split-brain
TC-607 | Proxy node failure | Proxy HA | Kill 1 proxy instance | HAProxy routes to others |  | Not Run | P1 |  |  | Zero downtime
TC-608 | All proxies down | Proxy HA | Kill all proxies | Connection refused |  | Not Run | P1 |  |  | Graceful error
TC-609 | Dashboard failover | Dashboard HA | Primary dashboard down | Proxies use secondary |  | Not Run | P1 |  |  | URL list
TC-610 | Dashboard complete outage | Dashboard HA | Both dashboards down | Proxies use cached config |  | Not Run | P1 |  |  | Fallback mode
TC-611 | Network partition healing | Network | Network restored | Cluster converges |  | Not Run | P2
TC-612 | Replica lag handling | Replication | Replica >10s behind | Proxy stops routing reads |  | Not Run | P2 |  |  | If R/W split
TC-613 | Redis crash recovery | Recovery | Redis restart | Loads RDB/AOF correctly |  | Not Run | P1
TC-614 | Proxy graceful shutdown | Deployment | SIGTERM to proxy | Drains connections |  | Not Run | P2
TC-615 | Zero-downtime proxy upgrade | Operations | Rolling upgrade 5 proxies | No client errors |  | Not Run | P1

## Test Execution Log
Execution # | Date | Tester | Environment | Total Tests | Passed | Failed | Pass Rate | Duration (hrs) | Notes
1 |  |  | Lab |  |  |  | 0% |  | Initial test run
2 |  |  | Staging |  |  |  | 0% |  | Pre-production validation
3 |  |  | Production |  |  |  | 0% |  | Production smoke test

## Reference - Commands
CAMELLIA SUPPORTED REDIS COMMANDS REFERENCE
Category | Command | Support Level | Notes | Test Coverage
String | GET, SET, INCR, DECR, APPEND | Full | All basic string ops | TC-001 to TC-010
String | MGET, MSET | Full | Use hash tags for cross-shard | TC-101 to TC-104
Hash | HGET, HSET, HGETALL, HDEL | Full | Standard hash operations | TC-011 to TC-014
List | LPUSH, RPUSH, LPOP, RPOP, LRANGE | Full | List operations | TC-015 to TC-019
Set | SADD, SMEMBERS, SINTER, SUNION | Full | SINTER needs hash tags | TC-020 to TC-109
Sorted Set | ZADD, ZRANGE, ZINTERSTORE | Full | Inter ops need hash tags | TC-023 to TC-111
Generic | EXISTS, DEL, EXPIRE, TTL | Full | Key management | TC-003 to TC-006
Generic | SCAN | Full | Cross-shard supported | TC-215
Generic | KEYS | Blocked | Dangerous in production | TC-216
Pub/Sub | PUBLISH, SUBSCRIBE | Partial | No custom sharding support | Not tested
Transaction | MULTI, EXEC | Partial | Same shard only | TC-115
Scripting | EVAL, EVALSHA | Full | Lua scripts supported | Not tested
Admin | CONFIG, FLUSHDB, FLUSHALL | Blocked | Security restriction | Should be blocked
Streams | XADD, XREAD, XGROUP | Full | Redis Streams supported | Not tested
JSON | JSON.SET, JSON.GET | Full | RedisJSON module | Not tested
Search | FT.SEARCH, FT.CREATE | Full | RediSearch module | Not tested

## Reference - Topology
PRODUCTION TOPOLOGY REFERENCE
Component | Quantity | IP/Endpoint | Port | Purpose | HA Mode
HAProxy VIP | 1 | 10.0.1.100 | 6379 | Client entry point | Keepalived VRRP
HAProxy Nodes | 2 | 10.0.1.10-11 | 6379, 8404 | L4 load balancing | Active/Standby
Camellia Proxy | 5 | 10.0.2.11-15 | 6379, 16379 | Redis proxy & routing | Stateless cluster
Camellia Dashboard | 2 | 10.0.3.10-11 | 8080 | Control plane | Active/Active
MySQL (Dashboard) | 2 | 10.0.3.20-21 | 3306 | Config storage | Master/Slave
Redis Pool 1 | 6 | 10.1.10.10-103 | 6379, 26379 | 1M+2R+3S | Sentinel HA
Redis Pool 2-10 | 54 | 10.1.20-100.* | 6379, 26379 | Same as Pool 1 | Sentinel HA
Prometheus | 1 | 10.0.4.10 | 9090 | Metrics collection | Standalone
Grafana | 1 | 10.0.4.11 | 3000 | Dashboards | Standalone
Total Instances | 73 |  |  | Full production stack